## Agile Sprint 1 Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
SPRINT#1
User Story #1: As a user, I want to collect a large dataset of inspirational quotes so that meaningful analysis can be performed. | 3
Collect inspirational quotes dataset | 2 | Jiya | Completed | 20 | 5 | 5 | 5 | 3 | 2 | Yes
Verify dataset quality and format | 1 | Jiya | Completed | 10 | 2 | 2 | 1 | 2 | 3 | Yes
TOTAL |  |  |  | 30 | 7 | 7 | 6 | 5 | 5 | 0

## Agile Sprint 2 Backlog
o
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
| BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
SPRINT#2
| User Story #2: As a user, I want to clean and preprocess the text so that noise and unwanted symbols are removed. | 3
| Convert text to lowercase | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Remove punctuation and noise | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Split text into clean lines | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| TOTAL |  |  |  | 30 | 6 | 6 | 6 | 6 | 6 | 0
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint 3 Backlog
o
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
| BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
SPRINT #3
| User Story #3: As a User, I want to apply NLP-based rule so that identify positive and inspirational words | 2
| Define NLP rules using regex | 1 | Jiya | Completed | 10 | 2 | 2 | 1 | 3 | 2 | Yes
| Test rules on sample quotes | 1 | Jiya | Completed | 10 | 1 | 3 | 2 | 2 | 2 | Yes
| User Story #4: As a User, I want to calculate word frequencies so that to nderstand commonly used motivational words | 2
| Count positive words | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Combine results from chunks | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| User Story #7: As a User, I want to process text data in chunks so that large datasets can be handled efficiently | 2
| Process text data in chunks | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Implement chunking logic | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| User Story#8: As a User, I want to apply parallel processing so that reduce execution time. | 2
| Apply ThreadPoolExecutor | 2 | Jiya | Completed | 20 | 5 | 5 | 4 | 3 | 3 | yes
| TOTAL |  |  |  | 80 | 16 | 18 | 15 | 16 | 15 | 0
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Sprint 4 Backlog
o
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
| BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
SPRINT#4
| User Story#: As a User, I want to store processed results in CSV format so that results can be reused and shared. | 2
| Store results in CSV format | 1 | Jiya | Completed | 5 | 2 | 1 | 1 | 1 | 0 | Yes
| Save word frequency to CSV | 1 | Jiya | Completed | 5 | 1 | 1 | 1 | 1 | 1 | Yes
| User Story#13: As a User, I want to generate bar charts so that visualize word frequency clearly. | 3
| Generate bar chart for word frequency | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Label axes and titles clearly | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Verify bar chart accuracy with data | 0.5 | Jiya | Completed | 5 | 0 | 1 | 1 | 1 | 2 | Yes
| Review visualization readability | 0.5 | Jiya | Completed | 5 | 0 | 1 | 1 | 1 | 2 | Yes
| User Story#9: As a User, I want to save results in a database so that data can be stored persistently. | 3
| Create SQLite database for results | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Insert processed word frequency data | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Verify data is stored correctly | 0.5 | Jiya | Completed | 5 | 2 | 1 | 1 | 1 | 0 | Yes
| Check database retrieval functionality | 0.5 | Jiya | Completed | 5 | 2 | 1 | 1 | 1 | 0 | Yes
| User Story#10: As a User, I want to generate pie chart visualization so that compare word distribution easily. | 3
| Generate pie chart for top positive words | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Display percentage distribution clearly | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 2 | 2 | Yes
| Verify pie chart accuracy with data | 1 | Jiya | Completed | 10 | 2 | 2 | 2 | 22 | 2 | Yes
| TOTAL |  |  |  | 100 | 21 | 20 | 20 | 40 | 19 | 0
CLICK HERE TO CREATE IN SMARTSHEET